## 90-Day Marketing Schedule
Tender Trimesters — 90-Day Day-by-Day Marketing Schedule
Mommies Matter ¦ Launch: August 15, 2026 ¦ Helena-Ann Baker
Phase | Date | Day | Content Type | Platform | Task Detail | CTA / Message | Asset Needed | KPI Target | Status
Pre-Launch | 2026-08-01 | Sat | Product/BTS | Instagram | Post first teaser: silhouette of app with 'Something beautiful is growing' text overlay. Use brand gradient moss-to-rose-gold background. | Save this post — link in bio coming soon | Teaser image (Canva), brand gradient background | Impressions > 500, Saves > 50 | To Do
Pre-Launch | 2026-08-02 | Sun | Rest Day | — | Rest and prepare content batch for the week. Review all 30 social captions from the content kit and schedule in Meta Business Suite. | — | Content kit docx, Meta Business Suite | Schedule 5 posts for next week | To Do
Pre-Launch | 2026-08-03 | Mon | Affirmation | Instagram Stories + TikTok | Post affirmation card: 'You are already the mother your child needs.' Show card from affirmation-cards.pdf with soft blush background. | Share with a mama who needs this today | Affirmation card image (Week 20 card from PDF) | Story views > 300, Shares > 20 | To Do
Pre-Launch | 2026-08-04 | Tue | Educational | Instagram Reels + TikTok | Reel: '3 things nobody tells you about your first trimester' — text-on-screen with voiceover. Mention Tempie AI as the supportive companion. | Follow for more pregnancy truths — link in bio | 15-sec reel video, teleprompter script | Views > 1000, Follows > 30 | To Do
Pre-Launch | 2026-08-05 | Wed | Engagement | Instagram | Carousel: 'What week are you?' — Week 1-40 slide showing baby size comparisons from the app. Ask followers to comment their week. | Comment your week below — tell us your baby's current size! | Carousel graphics (10 slides, baby fruit/veg comparisons) | Comments > 100, Engagement rate > 5% | To Do
Pre-Launch | 2026-08-06 | Thu | Product/BTS | Instagram + Facebook | BTS post: Show behind-the-scenes of building Tender Trimesters. Helena-Ann's story — why she built this app. Photo of workspace with app on screen. | This is personal. Link in bio to join the waitlist. | BTS photo, Helena-Ann headshot, app screenshot | Link clicks > 50, Waitlist signups > 20 | To Do
Pre-Launch | 2026-08-07 | Fri | Email | Email (ConvertKit/Mailchimp) | Send Email #1 of nurture sequence: 'Welcome to the village, mama' — introduce Helena-Ann, share her 'why', soft CTA to waitlist. | Join the waitlist — be first to try Tender Trimesters free | Email template in launch-announcement.docx | Open rate > 40%, CTR > 8% | To Do
Pre-Launch | 2026-08-08 | Sat | Product/BTS | TikTok + Instagram Reels | Video: Screen recording walkthrough of the app — show HomeScreen with week tracker, Tempie AI chat, calendar view. Add voiceover explaining each feature. | Waitlist is open — link in bio | Screen recording (2 min), Loom or OBS, voiceover script | Views > 2000, Waitlist signups > 30 | To Do
Pre-Launch | 2026-08-09 | Sun | Rest Day | — | Batch create next week's content. Write 5 more captions, design 3 affirmation graphics. Prepare influencer outreach emails from influencer-outreach.docx. | — | Canva Pro, content kit, influencer outreach templates | 5 posts ready, 10 outreach emails drafted | To Do
Pre-Launch | 2026-08-10 | Mon | Affirmation | Instagram Stories | Story series (3 slides): 'Your body knows what to do. Trust it.' — Week 28 affirmation card with baby size (eggplant). Final slide: waitlist CTA. | Join the waitlist — Link in bio | Affirmation card image, link sticker | Story taps > 200, Link taps > 30 | To Do
Pre-Launch | 2026-08-11 | Tue | Educational | Instagram + Pinterest | Infographic carousel: 'Your pregnancy hormones explained' — based on Hormone Horoscope feature. 8 slides covering hCG, progesterone, relaxin, oxytocin. | Save this for when those hormones hit — and download the app for weekly updates | Infographic (8 slides), Hormone Horoscope data from app | Saves > 200, Pins > 50 | To Do
Pre-Launch | 2026-08-12 | Wed | Engagement | Instagram | Poll sticker: 'What's your biggest pregnancy fear right now?' — 4 options (labor pain, body changes, not bonding, something going wrong). Use results to create content. | Vote below — we're building something to help with exactly this | Instagram poll sticker, branded background | Votes > 200, Profile visits > 50 | To Do
Pre-Launch | 2026-08-13 | Thu | Email | Email (ConvertKit/Mailchimp) | Send Email #2: Helena-Ann's story — 'I was scared too' — personal narrative about pregnancy anxiety, how Tempie was born from that fear. CTA: waitlist. | Read my full story — and join the waitlist | Email template in launch-announcement.docx, personal photos | Open rate > 45%, Replies > 20 | To Do
Pre-Launch | 2026-08-14 | Fri | Product/BTS | All platforms | LAUNCH EVE POST: 'Tomorrow, everything changes for mamas.' Countdown graphic. Reveal app icon. Final waitlist push. Share in all pregnancy Facebook groups. | Waitlist closes at midnight — be there when we launch | Countdown graphic (Canva), app icon, Facebook group posts | Waitlist signups > 100 total, Shares > 50 | To Do
Launch Week | 2026-08-15 | Sat | Launch Day | All platforms | LAUNCH DAY: Go live on Vercel. Post launch announcement across all channels. Instagram: 'It's HERE.' with app store link. TikTok: 30-sec hype video. Facebook: full announcement post. Email #3 to waitlist: 'It's live.' | Download Tender Trimesters FREE — tell every mama you know | Launch graphics (3 sizes), app store screenshots, email blast template | 500+ app signups Day 1, 1000+ website visits | To Do
Launch Week | 2026-08-16 | Sun | Engagement | Instagram Stories | Story: 'Show us your screen!' — ask new users to share screenshots of their app home screen (week tracker). Repost the best ones. Give shoutouts. | Tag us in your screenshot — we're reposting mamas all day | Story template with 'Show us your screen' text | User-generated content > 10 posts, Story views > 500 | To Do
Launch Week | 2026-08-17 | Mon | Affirmation | Instagram + TikTok | Post Week 12 affirmation: 'You are building a whole human. That is enough.' Tie to first-trimester-checklist.pdf lead magnet — 'Free download in bio.' | Download your free first trimester survival kit — link in bio | Affirmation card, first-trimester-checklist.pdf | Downloads > 100, Follows > 40 | To Do
Launch Week | 2026-08-18 | Tue | Educational | Instagram Reels + TikTok | Reel: 'How AI is changing pregnancy support' — show Tempie chat in action. Screen record a real conversation where Tempie responds to 'I'm scared of labor.' | Try Tempie free — link in bio | Screen recording (45 sec), Tempie chat demo | Views > 3000, App signups > 50 | To Do
Launch Week | 2026-08-19 | Wed | Partnership | Email + DMs | Send 10 influencer outreach emails (doulas, pregnancy influencers, mom bloggers). Use templates from influencer-outreach.docx. Follow up with DMs on Instagram. | Partnership inquiry — let's collaborate | Influencer outreach templates, partnership pitch one-pager | 10 emails sent, 3 responses | To Do
Launch Week | 2026-08-20 | Thu | Product/BTS | Instagram + Facebook | Post user testimonials: 'What mamas are saying about Tender Trimesters' — screenshot any early reviews/ratings. If none yet, share Helena-Ann's personal review of using the app. | Have you tried it yet? Download free — link in bio | Testimonial graphics, star rating images | Engagement rate > 6%, Link clicks > 80 | To Do
Launch Week | 2026-08-21 | Fri | Email | Email (ConvertKit/Mailchimp) | Send Email #4: Testimonial spotlight — feature a beta user story (or Helena-Ann's own). Introduce Premium features. Soft pitch: $9.99 one-time. | Unlock everything for $9.99 — or try the free version first | Email template, premium feature list, pricing graphic | Open rate > 40%, Premium conversions > 5 | To Do
Week 2: Growth | 2026-08-22 | Sat | Affirmation | Instagram Stories | Saturday affirmation series — post 3 story slides with handwritten-style affirmation from the app. Use Dancing Script font on blush background. | Share with a mama who needs this | 3 affirmation graphics (Stories size) | Story views > 400 | To Do
Week 2: Growth | 2026-08-23 | Sun | Rest Day | — | Content batching day: Write next 7 days of captions. Design 5 new graphics. Review analytics from Week 1 — what performed best? Double down on that format. | — | Analytics dashboard, Canva, caption template | 7 posts scheduled, analytics reviewed | To Do
Week 2: Growth | 2026-08-24 | Mon | Educational | Instagram + Pinterest | Carousel: 'Fear to Flame — how to reframe pregnancy anxiety' — walkthrough of the app feature. Explain the 3 stages: Ember, Spark, Flame. | This feature changed how I process fear — try it free | Feature walkthrough graphics (6 slides) | Saves > 150, App signups > 30 | To Do
Week 2: Growth | 2026-08-25 | Tue | Engagement | Instagram | 'Fill in the blank: Before I got pregnant, I wish someone told me ___' — engage comments, reply to every single one personally. This builds community. | Drop your answer below — let's talk about it | Branded engagement graphic | Comments > 150, Reply rate > 80% | To Do
Week 2: Growth | 2026-08-26 | Wed | Product/BTS | TikTok + Reels | Video: 'What's inside the Name Garden?' — show the name suggestion themes, the 'plant a seed' feature, chosen name celebration. Fun and light. | Find your baby's name in the app — free | Screen recording (60 sec), name garden demo | Views > 2000, App opens > 40 | To Do
Week 2: Growth | 2026-08-27 | Thu | Email | Email | Send Email #5: 'Your baby wrote you a letter' — showcase Letters from Baby feature. Include a sample AI-generated letter. CTA: generate your first letter. | Read your baby's letter — it's free in the app | Sample letter screenshot, email template | Open rate > 35%, App opens > 60 | To Do
Week 2: Growth | 2026-08-28 | Fri | Paid Ads | Meta Ads (Facebook + Instagram) | Launch first paid campaign: $10/day budget. Target: pregnant women 22-38, interest in pregnancy apps, baby names, meditation. Creative: testimonial-style video. | Download free — Tender Trimesters | Ad creative (video), Meta Ads Manager setup | CPA < $3, 50+ installs from ads | To Do
Week 3: Momentum | 2026-08-29 | Sat | Affirmation | TikTok + Instagram | TikTok trend: 'Tell me you're pregnant without telling me you're pregnant' — use app screenshots as reveal. Pair with trending audio. | Tag a pregnant mama — she needs this app | TikTok video (15 sec), trending audio | Views > 5000, Follows > 100 | To Do
Week 3: Momentum | 2026-08-30 | Sun | Rest Day | — | Plan Week 4 content. Review paid ad performance — adjust targeting if CPA > $5. Reach out to 5 more influencers. Follow up with previous outreach. | — | Ad analytics, influencer tracker, content calendar | Ads optimized, 5 follow-ups sent | To Do
Week 3: Momentum | 2026-08-31 | Mon | Educational | Instagram + Blog | Deep-dive post: 'Understanding your pregnancy dreams' — tie to DreamKeeper feature. Explain common pregnancy dream themes (water, birth, animals). CTA: start logging dreams. | Your dreams mean something — start capturing them | Long-form caption (200+ words), dream theme graphics | Saves > 200, DreamKeeper feature opens > 50 | To Do
Week 3: Momentum | 2026-09-01 | Tue | Engagement | Instagram | 'This or That: Pregnancy Edition' — 10 slides of pregnancy choices (find out gender vs surprise, epidural vs natural, etc.). High engagement format. | Save your results and tag a pregnant friend | This or That carousel (10 slides) | Engagement rate > 7%, Shares > 80 | To Do
Week 3: Momentum | 2026-09-02 | Wed | Partnership | Email + DMs | Follow up with all influencers who haven't responded. Send partnership pitch to 5 local doulas/midwives. Offer free Premium in exchange for honest review. | Free Premium access for honest review | Partnership follow-up templates, Premium access codes | 5 new partnerships initiated | To Do
Week 3: Momentum | 2026-09-03 | Thu | Product/BTS | Instagram + TikTok | Feature spotlight: Memory Capsule — 'Seal a memory for your child to open someday.' Show the create flow, unlock options (1yr, 5yr, 18th birthday). Emotional appeal. | What would you seal for your baby? Try it free | Feature demo video (45 sec), memory capsule screenshots | Views > 2500, Feature opens > 60 | To Do
Week 3: Momentum | 2026-09-04 | Fri | Email | Email | Weekly digest email: 'This week in your pregnancy' — dynamic content based on user's week. Include affirmation, tip, and feature spotlight. | Open the app for your full weekly update | Email template, dynamic content logic | Open rate > 35%, App opens > 100 | To Do
Week 4: Scale | 2026-09-05 | Sat | Affirmation | Instagram Stories | Weekend affirmation: 'You don't have to do this perfectly. You just have to do it.' Story poll: 'What's your self-care today?' with options. | Tell us your self-care below | Affirmation graphic, poll sticker | Story taps > 500, Poll votes > 200 | To Do
Week 4: Scale | 2026-09-06 | Sun | Rest Day | — | Monthly review: Pull all analytics. Calculate: total signups, conversion rate, top content, best platform, ad ROAS. Adjust month 2 strategy. | — | Analytics from all platforms, spreadsheet for tracking | Monthly report completed | To Do
Week 4: Scale | 2026-09-07 | Mon | Educational | Pinterest + Instagram | Pin 10 pregnancy-related infographics to Pinterest (hormone horoscope, fear stages, dream meanings). Each pin links to blog or app landing page. | Follow us on Pinterest for weekly pregnancy guides | 10 Pinterest graphics (1000x1500px), pin descriptions with keywords | Pinterest impressions > 5000, Clicks > 100 | To Do
Week 4: Scale | 2026-09-08 | Tue | Engagement | Instagram | 'Ask me anything about pregnancy' — go live on Instagram for 20 min. Answer questions about the app, pregnancy tips, share personal stories. Save to Highlights. | Join us live — ask anything | IG Live setup, promo story 1hr before | Live viewers > 50, Story replay views > 300 | To Do
Week 4: Scale | 2026-09-09 | Wed | Product/BTS | TikTok + Reels | Video: 'Build your birth playlist in the app' — show Birth Playlist feature, play song suggestions for each phase (early labor, active labor, pushing, golden hour). | What songs are on your birth playlist? Tell us below | Birth playlist demo (60 sec), song list graphic | Views > 3000, Comments > 100 | To Do
Week 4: Scale | 2026-09-10 | Thu | Paid Ads | Meta Ads | Scale winning ad creative. Create 2 new ad variations based on best-performing organic post. Increase budget to $15/day if CPA < $3. | Download Tender Trimesters free | New ad creatives (2 variations), Meta Ads Manager | CPA < $2.50 (improved), 80+ installs from ads | To Do
Week 4: Scale | 2026-09-11 | Fri | Email | Email | Month 1 wrap-up: 'What a month, mamas' — share stats (users joined, letters generated, fears reframed). Feature 2-3 user testimonials. Premium upsell. | You've made this first month incredible — here's what's next | Email template, user testimonials, stats graphic | Open rate > 35%, Premium conversions > 3% | To Do
Week 4: Scale | 2026-09-12 | Sat | Affirmation | Instagram + TikTok | Affirmation video: Helena-Ann reads an affirmation from the app in her own voice. Soft, warm, personal. 'You are enough, mama.' Loopable for TikTok. | Follow for daily affirmations for your pregnancy journey | Video of Helena-Ann (30 sec), mic setup, quiet space | Views > 4000, Follows > 80 | To Do
Week 4: Scale | 2026-09-13 | Sun | Rest Day | — | Plan Month 2 content calendar. Identify top 5 performing posts and recreate with variations. Draft 2 new lead magnets (second trimester checklist, fear journal). | — | Analytics, content calendar template, Canva | Month 2 plan ready, 2 lead magnets outlined | To Do
Week 5: Sustain | 2026-09-12 | Mon | Affirmation | Instagram Stories + TikTok | Weekly affirmation post — rotate through app affirmation cards. Share on Stories with interactive poll sticker. | Share with a mama who needs this today | Recycled from content bank | — | To Do
Week 5: Sustain | 2026-09-13 | Tue | Educational | Instagram + Pinterest | Educational carousel or reel — pregnancy tips, feature deep-dives, hormone insights, dream analysis. | Save this and share with your due-date group | Recycled from content bank | — | To Do
Week 5: Sustain | 2026-09-14 | Wed | Engagement | Instagram | Interactive content — polls, quizzes, this-or-that, Q&A, fill-in-the-blank. Reply to every comment. | Comment below — we read and reply to every single one | Recycled from content bank | Engagement rate > 5% | To Do
Week 5: Sustain | 2026-09-15 | Thu | Product/BTS | TikTok + Instagram Reels | Feature spotlight video — screen record one premium feature. Show real usage. Emotional storytelling. | Try this feature free — link in bio | Recycled from content bank | — | To Do
Week 5: Sustain | 2026-09-16 | Fri | Email | Email | Weekly digest or nurture email — rotate between: weekly update, feature spotlight, user testimonial, Helena-Ann's letter. | Open the app for your full weekly update | Email template | Open rate > 30%, App opens > 80 | To Do
Week 5: Sustain | 2026-09-17 | Sat | Affirmation + Paid Ads | Instagram + Meta Ads | Affirmation post + manage paid ads. Review ad performance, adjust budgets, create new creatives as needed. | Follow for daily pregnancy affirmations | Ad creatives, Meta Ads Manager | CPA < $2.50, 100+ weekly installs from ads | To Do
Week 5: Sustain | 2026-09-18 | Sun | Rest Day | — | Content batching, analytics review, influencer follow-ups, strategy planning for next week. | — | — | — | To Do
Week 6: Sustain | 2026-09-19 | Mon | Affirmation | Instagram Stories + TikTok | Weekly affirmation post — rotate through app affirmation cards. Share on Stories with interactive poll sticker. | Share with a mama who needs this today | Recycled from content bank | — | To Do
Week 6: Sustain | 2026-09-20 | Tue | Educational | Instagram + Pinterest | Educational carousel or reel — pregnancy tips, feature deep-dives, hormone insights, dream analysis. | Save this and share with your due-date group | Recycled from content bank | — | To Do
Week 6: Sustain | 2026-09-21 | Wed | Engagement | Instagram | Interactive content — polls, quizzes, this-or-that, Q&A, fill-in-the-blank. Reply to every comment. | Comment below — we read and reply to every single one | Recycled from content bank | Engagement rate > 5% | To Do
Week 6: Sustain | 2026-09-22 | Thu | Product/BTS | TikTok + Instagram Reels | Feature spotlight video — screen record one premium feature. Show real usage. Emotional storytelling. | Try this feature free — link in bio | Recycled from content bank | — | To Do
Week 6: Sustain | 2026-09-23 | Fri | Email | Email | Weekly digest or nurture email — rotate between: weekly update, feature spotlight, user testimonial, Helena-Ann's letter. | Open the app for your full weekly update | Email template | Open rate > 30%, App opens > 80 | To Do
Week 6: Sustain | 2026-09-24 | Sat | Affirmation + Paid Ads | Instagram + Meta Ads | Affirmation post + manage paid ads. Review ad performance, adjust budgets, create new creatives as needed. | Follow for daily pregnancy affirmations | Ad creatives, Meta Ads Manager | CPA < $2.50, 100+ weekly installs from ads | To Do
Week 6: Sustain | 2026-09-25 | Sun | Rest Day | — | Content batching, analytics review, influencer follow-ups, strategy planning for next week. | — | — | — | To Do
Week 7: Sustain | 2026-09-26 | Mon | Affirmation | Instagram Stories + TikTok | Weekly affirmation post — rotate through app affirmation cards. Share on Stories with interactive poll sticker. | Share with a mama who needs this today | Recycled from content bank | — | To Do
Week 7: Sustain | 2026-09-27 | Tue | Educational | Instagram + Pinterest | Educational carousel or reel — pregnancy tips, feature deep-dives, hormone insights, dream analysis. | Save this and share with your due-date group | Recycled from content bank | — | To Do
Week 7: Sustain | 2026-09-28 | Wed | Engagement | Instagram | Interactive content — polls, quizzes, this-or-that, Q&A, fill-in-the-blank. Reply to every comment. | Comment below — we read and reply to every single one | Recycled from content bank | Engagement rate > 5% | To Do
Week 7: Sustain | 2026-09-29 | Thu | Product/BTS | TikTok + Instagram Reels | Feature spotlight video — screen record one premium feature. Show real usage. Emotional storytelling. | Try this feature free — link in bio | Recycled from content bank | — | To Do
Week 7: Sustain | 2026-09-30 | Fri | Email | Email | Weekly digest or nurture email — rotate between: weekly update, feature spotlight, user testimonial, Helena-Ann's letter. | Open the app for your full weekly update | Email template | Open rate > 30%, App opens > 80 | To Do
Week 7: Sustain | 2026-10-01 | Sat | Affirmation + Paid Ads | Instagram + Meta Ads | Affirmation post + manage paid ads. Review ad performance, adjust budgets, create new creatives as needed. | Follow for daily pregnancy affirmations | Ad creatives, Meta Ads Manager | CPA < $2.50, 100+ weekly installs from ads | To Do
Week 7: Sustain | 2026-10-02 | Sun | Rest Day | — | Content batching, analytics review, influencer follow-ups, strategy planning for next week. | — | — | — | To Do
Week 8: Sustain | 2026-10-03 | Mon | Affirmation | Instagram Stories + TikTok | Weekly affirmation post — rotate through app affirmation cards. Share on Stories with interactive poll sticker. | Share with a mama who needs this today | Recycled from content bank | — | To Do
Week 8: Sustain | 2026-10-04 | Tue | Educational | Instagram + Pinterest | Educational carousel or reel — pregnancy tips, feature deep-dives, hormone insights, dream analysis. | Save this and share with your due-date group | Recycled from content bank | — | To Do
Week 8: Sustain | 2026-10-05 | Wed | Engagement | Instagram | Interactive content — polls, quizzes, this-or-that, Q&A, fill-in-the-blank. Reply to every comment. | Comment below — we read and reply to every single one | Recycled from content bank | Engagement rate > 5% | To Do
Week 8: Sustain | 2026-10-06 | Thu | Product/BTS | TikTok + Instagram Reels | Feature spotlight video — screen record one premium feature. Show real usage. Emotional storytelling. | Try this feature free — link in bio | Recycled from content bank | — | To Do
Week 8: Sustain | 2026-10-07 | Fri | Email | Email | Weekly digest or nurture email — rotate between: weekly update, feature spotlight, user testimonial, Helena-Ann's letter. | Open the app for your full weekly update | Email template | Open rate > 30%, App opens > 80 | To Do
Week 8: Sustain | 2026-10-08 | Sat | Affirmation + Paid Ads | Instagram + Meta Ads | Affirmation post + manage paid ads. Review ad performance, adjust budgets, create new creatives as needed. | Follow for daily pregnancy affirmations | Ad creatives, Meta Ads Manager | CPA < $2.50, 100+ weekly installs from ads | To Do
Week 8: Sustain | 2026-10-09 | Sun | Rest Day | — | Content batching, analytics review, influencer follow-ups, strategy planning for next week. | — | — | — | To Do
Week 9: Expand | 2026-10-10 | Mon | Partnership | Email + DMs | Week of partnership outreach — contact 5 new influencers, doulas, or birth educators. Send review copies of Premium. | Free Premium for honest review — DM us | Partnership templates | 5+ new partnerships/week | To Do
Week 9: Expand | 2026-10-11 | Tue | Educational | All platforms | Long-form content: blog post or video essay on a pregnancy topic. Repurpose into 5+ micro-content pieces for social. | Read the full guide — link in bio | Content repurposed from blog/video | — | To Do
Week 9: Expand | 2026-10-12 | Wed | Engagement | Instagram | Community-building content — user spotlight, 'mama of the week,' partner feature, bump photo showcase. | Tag us to be featured — we celebrate every mama | Content repurposed from blog/video | — | To Do
Week 9: Expand | 2026-10-13 | Thu | Product/BTS | TikTok + Reels | New feature announcement or update showcase. If no new features, show a 'day in the life' using the app. | Update your app for the latest features | Content repurposed from blog/video | — | To Do
Week 9: Expand | 2026-10-14 | Fri | Email | Email | Monthly newsletter: top tips, user stories, new features, premium offer. Segment: free users vs premium. | See what's new this month — and unlock premium | Monthly newsletter template | Open rate > 30%, Premium upsell > 2% | To Do
Week 9: Expand | 2026-10-15 | Sat | Affirmation + Paid Ads | Instagram + Meta Ads | Affirmation + paid ads management. A/B test new ad creatives. Scale budget if ROAS > 3x. | Follow for daily affirmations | New ad creatives (A/B test), Meta Ads Manager | ROAS > 3x, Scale to $25/day if profitable | To Do
Week 9: Expand | 2026-10-16 | Sun | Rest Day | — | Strategic review: update 90-day plan, set new KPIs, plan next quarter's content themes and partnership goals. | — | — | — | To Do
Week 10: Expand | 2026-10-17 | Mon | Partnership | Email + DMs | Week of partnership outreach — contact 5 new influencers, doulas, or birth educators. Send review copies of Premium. | Free Premium for honest review — DM us | Partnership templates | 5+ new partnerships/week | To Do
Week 10: Expand | 2026-10-18 | Tue | Educational | All platforms | Long-form content: blog post or video essay on a pregnancy topic. Repurpose into 5+ micro-content pieces for social. | Read the full guide — link in bio | Content repurposed from blog/video | — | To Do
Week 10: Expand | 2026-10-19 | Wed | Engagement | Instagram | Community-building content — user spotlight, 'mama of the week,' partner feature, bump photo showcase. | Tag us to be featured — we celebrate every mama | Content repurposed from blog/video | — | To Do
Week 10: Expand | 2026-10-20 | Thu | Product/BTS | TikTok + Reels | New feature announcement or update showcase. If no new features, show a 'day in the life' using the app. | Update your app for the latest features | Content repurposed from blog/video | — | To Do
Week 10: Expand | 2026-10-21 | Fri | Email | Email | Monthly newsletter: top tips, user stories, new features, premium offer. Segment: free users vs premium. | See what's new this month — and unlock premium | Monthly newsletter template | Open rate > 30%, Premium upsell > 2% | To Do
Week 10: Expand | 2026-10-22 | Sat | Affirmation + Paid Ads | Instagram + Meta Ads | Affirmation + paid ads management. A/B test new ad creatives. Scale budget if ROAS > 3x. | Follow for daily affirmations | New ad creatives (A/B test), Meta Ads Manager | ROAS > 3x, Scale to $25/day if profitable | To Do
Week 10: Expand | 2026-10-23 | Sun | Rest Day | — | Strategic review: update 90-day plan, set new KPIs, plan next quarter's content themes and partnership goals. | — | — | — | To Do
Week 11: Expand | 2026-10-24 | Mon | Partnership | Email + DMs | Week of partnership outreach — contact 5 new influencers, doulas, or birth educators. Send review copies of Premium. | Free Premium for honest review — DM us | Partnership templates | 5+ new partnerships/week | To Do
Week 11: Expand | 2026-10-25 | Tue | Educational | All platforms | Long-form content: blog post or video essay on a pregnancy topic. Repurpose into 5+ micro-content pieces for social. | Read the full guide — link in bio | Content repurposed from blog/video | — | To Do
Week 11: Expand | 2026-10-26 | Wed | Engagement | Instagram | Community-building content — user spotlight, 'mama of the week,' partner feature, bump photo showcase. | Tag us to be featured — we celebrate every mama | Content repurposed from blog/video | — | To Do
Week 11: Expand | 2026-10-27 | Thu | Product/BTS | TikTok + Reels | New feature announcement or update showcase. If no new features, show a 'day in the life' using the app. | Update your app for the latest features | Content repurposed from blog/video | — | To Do
Week 11: Expand | 2026-10-28 | Fri | Email | Email | Monthly newsletter: top tips, user stories, new features, premium offer. Segment: free users vs premium. | See what's new this month — and unlock premium | Monthly newsletter template | Open rate > 30%, Premium upsell > 2% | To Do
Week 11: Expand | 2026-10-29 | Sat | Affirmation + Paid Ads | Instagram + Meta Ads | Affirmation + paid ads management. A/B test new ad creatives. Scale budget if ROAS > 3x. | Follow for daily affirmations | New ad creatives (A/B test), Meta Ads Manager | ROAS > 3x, Scale to $25/day if profitable | To Do
Week 11: Expand | 2026-10-30 | Sun | Rest Day | — | Strategic review: update 90-day plan, set new KPIs, plan next quarter's content themes and partnership goals. | — | — | — | To Do
Week 12: Expand | 2026-10-31 | Mon | Partnership | Email + DMs | Week of partnership outreach — contact 5 new influencers, doulas, or birth educators. Send review copies of Premium. | Free Premium for honest review — DM us | Partnership templates | 5+ new partnerships/week | To Do
Week 12: Expand | 2026-11-01 | Tue | Educational | All platforms | Long-form content: blog post or video essay on a pregnancy topic. Repurpose into 5+ micro-content pieces for social. | Read the full guide — link in bio | Content repurposed from blog/video | — | To Do
Week 12: Expand | 2026-11-02 | Wed | Engagement | Instagram | Community-building content — user spotlight, 'mama of the week,' partner feature, bump photo showcase. | Tag us to be featured — we celebrate every mama | Content repurposed from blog/video | — | To Do
Week 12: Expand | 2026-11-03 | Thu | Product/BTS | TikTok + Reels | New feature announcement or update showcase. If no new features, show a 'day in the life' using the app. | Update your app for the latest features | Content repurposed from blog/video | — | To Do
Week 12: Expand | 2026-11-04 | Fri | Email | Email | Monthly newsletter: top tips, user stories, new features, premium offer. Segment: free users vs premium. | See what's new this month — and unlock premium | Monthly newsletter template | Open rate > 30%, Premium upsell > 2% | To Do
Week 12: Expand | 2026-11-05 | Sat | Affirmation + Paid Ads | Instagram + Meta Ads | Affirmation + paid ads management. A/B test new ad creatives. Scale budget if ROAS > 3x. | Follow for daily affirmations | New ad creatives (A/B test), Meta Ads Manager | ROAS > 3x, Scale to $25/day if profitable | To Do
Week 12: Expand | 2026-11-06 | Sun | Rest Day | — | Strategic review: update 90-day plan, set new KPIs, plan next quarter's content themes and partnership goals. | — | — | — | To Do

## Content Type Legend
Content Type Color Legend
Content Type | Description | When to Use
Affirmation | Inspirational quotes, affirmation cards, emotional support content | Monday & Saturday — start and end the week with warmth
Educational | Pregnancy tips, feature deep-dives, infographics, hormone insights | Tuesday — mid-week value content that gets saved
Engagement | Polls, quizzes, Q&A, this-or-that, fill-in-the-blank, user spotlights | Wednesday — peak engagement day for comments
Product/BTS | App features, behind-the-scenes, screen recordings, testimonials | Thursday — showcase what makes Tender Trimesters special
Email | Nurture sequences, weekly digests, feature announcements, newsletters | Friday — end-of-week inbox presence
Partnership | Influencer outreach, doula/midwife partnerships, collaboration pitches | Week 3+ — once initial content foundation is set
Launch Day | All-hands marketing push across every channel simultaneously | Day 0 only — maximum visibility
Paid Ads | Meta Ads management, A/B testing, budget scaling, ROAS optimization | Week 2+ — after organic content proves what resonates
Rest Day | Content batching, analytics review, strategy planning, self-care | Every Sunday — prevent burnout, plan ahead

## Weekly KPI Tracker
Weekly KPI Tracker — Track Your Growth
Week | New Signups | Premium Conv. | Instagram Foll. | Email Subs | Ad Spend | Ad Installs | CPA | Top Platform | Notes
Week 1
Week 2
Week 3
Week 4
Week 5
Week 6
Week 7
Week 8
Week 9
Week 10
Week 11
Week 12
Week 13